## Sheet1
Type Key: Bug/Issue - Functionality did not work as expected or casues issues with workflow, development needed to resolve Enhancement - Functionality works as expected but enhancements would streamline workflow, these items will be considered for furture development Explanation - Functionality works as expected, explanation or guidance needed to move user forward, no development needed to resolve.
Topic | Issue Summary | Type | Status | Column5 | Resolution for Explanation Type Items
Topic | Issue Summary | Type | Status | Sub-status | Resolution for Explanation
Entity Mgt | Enhancement: Training programs under LWIA 0 | Enhancement
Customer List | Customers with no LWIA showing up for all LWIA filtering | Explanation | Resolved | Closed | Before an application is submitted a customer does not belong to an LWIA. Career Planners can view those so that customers can receive assistance as needed during intake. This is important for customers on boarding LWIAs.
Customer Settings | Career Planners showing with incorrect office | Explanation | Resolved | Closed | Users show associated with the entity tagged as a LWIA. Some legacy entities had duplicate locations, one associated for LWIA and one associated for providing services. All users are associated to the entities identified as an LWIA in IWDS 2.0
Conversion | Missing customers with self services and no applications | Bug | In Progress | In Development
Relationship Mgt | Missing LWIA office | Explanation | Resolved | Closed | These were inactive in legacy and IWDS 2.0 worked directly with LWIA so they could get those updated.
Career Plan | Youth Career Planning Service needs mapped to Career Awareness | Issue | Resolved | Released to Production
Relationship Mgt | Missing Providers | Explanation | Resolved | Closed | These were inactive in legacy and IWDS 2.0 worked directly with LWIA so they could get those updated.
Career Plan | Missing Cash Incentive association | Bug | Resolved | Released to Production
Career Plan | Reassociating Converted Steps | Explanation | Resolved | Closed | Technical guidance is being provided on re-aligning the career plan for active customers.This webinar provides more information on that process: https://youtu.be/UEiOlnumygQ?si=rtwTZeDD2ejz5cPT
Career Plan | Unable to backdate a training service start date | Issue | Resolved | Released to Production
Permissions | Intake and Pre-Screening issue | Bug | In Progress | In Development
Relationship Mgt | Entity missing in services | Explanation | Resolved | Closed | Missing/Inactive relationships. Once correctedthey display
Permissions | Permissions needed to view entities | Enhancement
Permissions | Digital SDA missing on first login | Enhancement |  |  | Working with Legal on this.
Permissions | User assigned Provider wrong permissions | Issue | Not Started | Backlog Item Created
Customer Settings | Career Planners unable to see customers | Explanation | Resolved | Closed | Some customers had inactive career planners associated with them or were blank. If there was not a matching career planner in the IWDS 2.0 user table the users had to realign those at go live. This webinar provides more information on that process: https://youtu.be/UEiOlnumygQ?si=rtwTZeDD2ejz5cPT at about 3:20 it goes over this process.
Conversion | Resume and Interview Prep Services not coming over from legacy IEP | Explanation | Resolved | Closed | Showed user how to view legacy IEP data.
Applications | Applications Export Truncates Data at 2,001 Rows, Omitting Customers Beyond "N" | Bug | In Progress | Developed | The applications export currently truncates at 2,000 rows, which may cause customers with last names past "N" to be missing in large caseloads. As a workaround, use the search or filter options within IWDS 2.0 to locate specific customers.
Conversion | April 2026 First-Week Certifications Missing After IWDS 2.0 Migration | Explanation | Resolved | Closed | We investigated and confirmed that customers certified in April 2026 were successfully migrated to IWDS 2.0. All sample customers were located with applications dated April 2026. If you are unable to locate a specific customer, please contact your LWIA administrator.
Applications | Self-Directed Pre-Screening Submission Blocked Due to Missing LWA Office Locations for Bentonville ZIP Cod | Bug | Resolved | Released to Production | Customers entering a Bentonville, IL zip code during self-directed pre-screening are unable to submit because no office locations appear. In the meantime, please have the customer contact your office directly to complete their application.
Reporting | Customer Unable to Select LWIA in Application Submit | Explanation | Resolved | Closed | All users can view customers in these rows until the application is submitted and associated with an LWIA. Customers who have an active prescreen that has not been fully completed will show in this row.
Relationships | User unable to log into IWDS 2.0 | Explanation | Resolved | Closed | The user's email address was confirmed correct in the system. The user should reset their password using their current Illinois workNet email address. If the issue continues, please contact your LWIA administrator.
Reporting | Report needed for Providers with Contact Information | Enhancement
Reporting | Report needed for Career Planners to track 1A customers | Enhancement |  | Response Still Needed | The Caseload Summary report currently shows total 1A/1D counts but does not yet break down 1A customers by priority subcategory. You will be notified when this report becomes available.
Applications | Application Errors Basic Skills and Selective Services | Bug | Resolved | Released to Production | The error preventing application submission when both basic skills/language and selective service validation errors appeared simultaneously has been resolved. Please retry the application submission.
Career Plan | Pirority of Service items do not require documentation | Explanation | Resolved | Closed | The system does not currently require documentation for priority of service items other than veteran. A change request was submitted to enhance the system to allow for that to be uploaded in to the system. Until that feature is avaiable staff should maintain paper documentation for priority of service items.
Reporting | Dashboard Update Frequency | Explanation | Resolved | Closed | The dashboard updates nightly. A date and time stamp in the top right corner of the page shows when it was last updated.
Reporting | Case Note Edits in Career Plan Create Duplicates in Case Notes Tab | Bug | Not Started | Backlog Item Created | A fix is in development.
ETPL | Enhancement: Program Search is only showing one record | Explanation | Resolved | Closed | Al to create an enhancement story.
Conversion | Data Migration - Missing Customer | Explanation | Resolved | Closed | Some CC custmomers were not migrated to IWDS legacy, thus they were not part of the IWDS 2.0 migration. LWIA 7 is working with the Career Planner to provide them the customer information so those can be added in.
Permissions | Access to Entity Management Request | Explanation | Resolved | Closed | Access provided to verified staff
Permissions | Unable to Access Training Assessment Access Denied | Issue | Not Started | Backlog Item Created
Permissions | Career Planner Missing in Search | Issue | Resolved | Released to Production
Self Services Entry | System duplicating Services | Explanation | Resolved | Closed | Guidance provided on adding self and information only services
Credentials | Adding a credential not added by training program | Explanation | Resolved | Closed | Walked thru the process with the user.
Career Plan | Services are closed, but employment retention support is continuing | Explanation | Resolved | Closed | Followed up and correct an error in my previous response. The estimated exit date is a hard exit date. The system will automatically exit a customer 90 days after their last service ends, looking only at services in Open status. Services in Planned or Not Started status do not prevent an automatic exit. If a customer has a future planned service with a start date more than 90 days away, the career planner should use the Pause option in Customer Settings to prevent the auto-exit.
Credentials | Manually Adding Credential and Date does not save | Bug | Not Started | Backlog Item Created | When manually typing a date into the credential date field, the date does not save correctly. As a workaround, please use the calendar icon to select the date, which saves as expected.
Manage Pending Registrations | Enhancement: Work Location to be filtered | Enhancement | Resolved | Responded
Assessments | Documents required for Associates degree | Explanation | Resolved | Closed | To document an associate's degree, you may upload a transcript, diploma, or use self-attestation.
User Roles - Career Planner | User not seeting customers | Explanation | Resolved | Closed | Per Mark's comment from 7/9 this is trade related. User was deactivated for now.
LWIA Assignment | User not seeting customers | Explanation | Resolved | Closed | Per Mark's comment from 7/9 this is trade related. User was deactivated for now.
Assessments | State Supplemental Grants not yet added to 2.0 | Explanation | Resolved | Closed | State supplemental grants are not yet managed in IWDS 2.0. They are still maintained in the Grants Reporting Form (GRF) in Illinois workNet.
Dashboard | Users cannot submit because office can be selected | Explanation | Resolved | Closed | User was able to submit application. Confrimed application submitted with local office
Reporting | Cannot export customer list from dashoard | Enhancement | Resolved | Closed | Laura confirmed the dashboard is not finished yet. These issues will likely be resolved when development is competed.
Reporting | Customer acticvity report includes customers in follow up | Enhancement | Resolved | Closed | Laura confirmed the dashboard is not finished yet. These issues will likely be resolved when development is competed.
Applications | Customers triggering incorrectly | Explanation | In Progress | In Development | The career planner page of the application includes a question to determine BSD based on assessment scores. If a score is entered that reflects basic skills deficiency, the customer will trigger for priority of service under that criterion.
Credentials | Providing entity missing | Issue | Resolved | Closed | Explained that the Providing entity isn't the accrediting body. But also other providing entities aren't available to choose.
Credentials | Expired Training Program | Issue | Resolved | Released to Production
Reporting | Dashboard issue with application closed prior to enrollment. | Bug | Not Started | Backlog Item Created
Applications | LWIA unable to upload documents for prescreening/application | Bug | Not Started | Backlog Item Created
GSA | LWIA unable to select entity and credential | Explanation | Resolved | Closed | You need to have an active relationship set up with the entitiy location that provides the Initial Comprensive Service. Do a hard refresh after adding the relationships.
Career Plan | Cannot add service to customer certified in 1.0 | Explanation | Resolved | Closed | Correct goal/service was added
Migration | Migrated customers missing documents | Issue | Not Started
Migration | Customer did not convert to 2.0 | Enhancement |  | Response Still Needed | This is a TAA customer and will be brought over when we migrate TAA data in the next few weeks.
Intake | Unable to add assessment in Application screen | Bug | Resolved | Released to Production
Intake | Users cannot submit because office can be selected | Explanation | Resolved | Closed | A required field was missing. Once corrected the application was able to be submitted.
ETPL Provider Access | Users unable to access ETPL | Bug | In Progress | In Development
Documents | Documents uploaded are getting migrated | Explanation | Resolved | Closed | Verified with user that documents being uploaded are migrating.
Career Plan | Cannot edit a migrated service date | Bug | In Progress | In Development
Career Plan | Cannot select funded button | Issue | In Progress | In Development
Dashboard | Dashboard issue | Explanation | Resolved | Closed | Let user know how to access dashboard from menu and that enhancements will be coming
Exits | Customer exit dates not migrating | Bug | Not Started | Backlog Item Created
Reporting | Customers listed on the dashboard incorrectly | Issue | Not Started | Closed
Reporting | Dashboard not filtering correctly | Issue | Not Started | Closed
Intake | Customers migrated incorrectly | Bug | Not Started | Backlog Item Created
Transition Date | Transition not showing correct dates or service | Bug | In Progress | In Development
Follow-Up | Follow-up summary has forced exit capacity | Bug | In Progress | In Development
Conversion | Services not available for 1Y customers | Bug | Resolved | Released to Production
Customer Settings | Unable to change the Primary CP | Bug | Not Started | Backlog Item Created
IL Worknet account | Users cannot submit because office can be selected | Bug | Not Started | Backlog Item Created
User Management | Users are seeing other users across the state | Bug | Not Started | Backlog Item Created
Intake Customer Channel | Users cannot submit because office can be selected | Bug | Resolved | Released to Production | Applied fix to remove the login requirement.
| ITA funded amount sent when less than the program | Explanation | Resolved | Closed | The amount is not entered in IWDS 2.0, we don't track that as a service by service basis.
Applications | Users cannot submit because office can be selected | Bug | In Progress | In Development | Customers in some areas are unable to submit their pre-screening application because office locations are not appearing when searching by zip code. In the meantime, please have the customer contact your office directly to complete their application.
ETPL provider access | Provider showing expired | Issue | Not Started | New | The system does not currently require documentation for priority of service items other than veteran. A change request was submitted to enhance the system to allow for that to be uploaded in to the system. Until that feature is avaiable staff should maintain paper documentation for priority of service items.
Applications | User unable to certify customer | Bug | Not Started | New | Out-of-state customers are eligible to be served. However, some local boards have set priorities to serve in-state customers first when funding is limited — check with your LWIA administrator for your local board's policy. A full street address is not a required reporting element, but state, county, and zip code are required and must be collected. The exception is for youth customers who may need to be determined to be living in a high-poverty area for eligibility — in that case, the full address should be collected and verified using the Census Bureau's website
Applications | Proof of Income not required for 1A customers | Explanation | Resolved | Closed | The system does not currently require documentation for priority of service items other than veteran. A change request was submitted to enhance the system to allow for that to be uploaded in to the system. Until that feature is avaiable staff should maintain paper documentation for priority of service items.
Applications | Other States: System not asking for proof of address | Explanation | Resolved | Closed | Out-of-state customers are eligible to be served. However, some local boards have set priorities to serve in-state customers first when funding is limited — check with your LWIA administrator for your local board's policy. A full street address is not a required reporting element, but state, county, and zip code are required and must be collected. The exception is for youth customers who may need to be determined to be living in a high-poverty area for eligibility — in that case, the full address should be collected and verified using the Census Bureau's website
Career Plan | Relationship not asked | Explanation | Resolved | Closed | A relationship was not set. Once that was set the issue was resolved.
Migration | Unable to exit customer | Explanation |  | Response Still Needed | Customers are auto exited in IWDS 2.0
Migration | Missing customer | Issue | Resolved | Closed | Customer Yvette Travino was not found in IWDS 1.0 or Career Connect. If this customer was served only in Career Connect without a record in IWDS 1.0, LWIA 7 will need to provide the customer's information to be entered manually into IWDS 2.0. Please contact your LWIA administrator for next steps.
Customer Search | Career Coaches missing from location filter | Bug | Not Started | New
Applications | Size error message when uploading SS document | Bug | Resolved | Released to Production | A file size error is occurring when uploading selective service documents. In the meantime, please contact your LWIA administrator for assistance with document submission.
Relationships | Institue showing with no relation to LWIA | Bug | Not Started | Backlog Item Created
Youth Customer | System missing service for Cash Incentives | Bug | Resolved | Released to Production
Career Planner Assign | User unable to locate and assign customer | Bug | Not Started | Backlog Item Created
Intake | User unable to see an application in their login | Issue | Not Started | Backlog Item Created
GSA | GSA Saving Issue | Issue | In Progress | In Development
Customer Search | Missing customer | Explanation | Resolved | Closed | Customer was not migrated from CC to IWDS 1.0 thus they were not migrated into IWDS 2.0. Worked with user to get them added into IWDS 2.0
ETPL | Training Program not showing for Add Assessment | Explanation | Resolved | Closed | The Assessment is added through a relationship update. It is the Comprehensive Assessment for each program. Then it is selectable in the dropdown.
User Role | Cannot remove access | Explanation | Resolved | Closed | User was deactivated and will be addressed as part of the Trade work
Customer | Participants not receiving inital email during application | Bug | In Progress | In Development
Case Note | Add new Category to Case Notes | Enhancement |  | Backlog Item Created
Application Blank | Dashboard > Application Cert. & Enrolling Services - applications showing blank | Explanation | Resolved | Closed | We did not migrate legacy application data into the new IWDS 2.0 application. A shell of their application, including certification data, was brought over and they will pick up from career planning in iWDS 2.0
ETPL | Users unable to search by State | Enhancement
Customer | Enhancement: Set and Save Search Favorite | Enhancement
User Roles | Use unable to maneuver system when impersonating a user | Explanation | Resolved | Closed | Yes, it sounds like you are impersonating a training provider who wouldn't have access to any of the other screens. You will be stuck in that role until you select your name from the dropdown and select to remove impersonation.
Training Assessment | Training & Education Assesment Required but voucher was provided during blackout and training assessment has already been done. | Issue | Resolved | Released to Production
GSA | GSA Saving Issue | Bug | In Progress | In Development
Customer Outcome | Institutions missing when adding an outcome | Enhancement
MSG Doc Upload | MSG Upload Error | Bug | Resolved | Released to Production
Add Assessment | User unable to add assessment and missing button | Bug | Not Started | New
Customer Search | User unable to see customer | Bug | Not Started | New
Dashboard Customers | All LWIAs Dashoard Customers - Closure Reason Other list | Enhancement
Career Plan | Updating Employment Goal is required | Explanation | Resolved | Response Still Needed | Currently the system will close them regardless of goal and step status. The auto exit closure is looking at no open services that extends enrollment for more than 90 days. More policy discussion can be had on this if needed.
Application | Unable to see customer application | Explanation | Resolved | Closed | Legacy application data was not migrated into IWDS 2.0. A summary of the customer's application, including certification data, was brought over. Customers will begin with career planning in IWDS 2.0 going forward.
Application | GSA Saving Issue | Bug | Resolved | Released to Production
Application | User unable to upload documents to application | Bug | In Progress | In Development
ETPL | User unable to access record or training programs | Bug | In Progress | In Development
Case Notes | User cannot see notes entered by other user | Bug | Not Started | Backlog Item Created
Case Load | Can't start Intake | Bug | In Progress | In Development
Self Services/Front Line Staff | Enhancement - More selections needed for customers | Enhancement
Customer | Active customer missing application | Issue | Not Started | Backlog Item Created
Service Episodes | Service episodes table missing from customer | Bug | Resolved | Released to Production
Case Notes | User cannot see notes entered by other user | Bug | Not Started | Backlog Item Created
Permissions | User Access showing denied | Bug | Not Started | Backlog Item Created
User Roles | Enhancement - Account Managers can filter by role | Enhancement
Application Submit | User unable to submit application without selecting Office and Career Planner | Explanation | Resolved | Response Still Needed | The customer facing application does not display the Support Staff Member on the submit page, the customer just has to select an office. When completing the application as an IWDS user then a Support Staff Member is required.
GSA | GSA Saving Issue | Bug | Not Started | Backlog Item Created
Career Plan | Process: How to close training and add credential | Explanation | Resolved | Responded | To close a training service and add a credential: open the training service, select Edit, change the status to Discontinued or Successful Completion, and add the end date. Once the service is closed, you can add the credential to the customer's record.
Conversion | User missing already exited customers | Explanation | Resolved | Responded | Customer was already exited.
Career Plan | User unable to add transportation supportive services | Bug | Resolved | Responded | This issue has been resolved. Aero is now available as a provider for supportive services in IWDS 2.0. Please try adding the transportation supportive service again and select Aero as the providing entity.
Career Plan | Error when adding a goal, step, and service | Bug | In Progress | Responded | The Technology and Communication Institute Cloud Computing RAP program is active and available in IWDS 2.0. CIP codes and ONET codes are not currently auto-populating from the program data, but both can be added manually using the search icon on the service form. The provider and program should be selectable. Bug card 22115 has been created to address the data transfer issue for CIP and ONET codes.
GSA | GSA and Household Income Verbiage | Enhancement
Application | Document Uploads in Application - File Size Error | Bug | Not Started | Backlog Item Created
ETPL Relationship | Training Provider Relationship Missing | Bug | Not Started | Backlog Item Created
ITA Voucher - Career Plan | LWIA 7 ITA status backdate | Issue | In Progress | In Development
Career Plan - Legacy | Is there a step by step guide on moving legacy services | Explanation | Resolved | Response Still Needed | We do not have a step by ste guide but this webinar provides more information on that process: https://youtu.be/UEiOlnumygQ?si=rtwTZeDD2ejz5cPT
Career Plan - Service | Career Pathway in 1.0 goes where in 2.0 | Explanation | In Progress | Response Still Needed
CASE NOTES - Career Plan | Case Notes Edits Not Displaying | Bug | Not Started | Backlog Item Created | Case Notes are tied to the service. You can view the case note history on a specific service in edit mode of that service or on the case note page. We will expand this so that you can access the case note history for the service on the view mode as well.
Intake | High Poverty Address Populating N/A and creating Block | Bug | Resolved | Released to Production
Career Plan - Service Date | Back Dating Service not allowing to go back further | Bug | Not Started | New
Intake | Customer Application Missing | Bug | Not Started | Backlog Item Created
ETPL Relationship | Training Provider Relationship Missing | Bug | Not Started | Backlog Item Created
Eligibility Cert Progress | Eligiblity Cetification Progress Bar Not Updating | Bug | Not Started | Backlog Item Created
Intake | Unable to trigger High Poverty Area Response | Bug | In Progress | Developed
Eligibility Certification | Unable to Certify for In School Youth | Bug | Not Started | Backlog Item Created
ETPL | Entity Missing In Providing Entity Drop Down | Bug | Not Started | Backlog Item Created
Eligibility Certification | No SNAP Benefit Document Upload Required | Bug | Not Started | Backlog Item Created
GSA Permission | Career Planner unable to access GSA | Bug | Resolved | Released to Production
GSA Providing Entity list | The providing entity list is empty | Explanation | Resolved | Response Still Needed | You need to have an active relationship set up with the entitiy location that provides the Initial Comprensive Service. Do a hard refresh after adding the relationships.
LWIA 7 ITA | Need to Reflect ITA Approved | Explanation | Resolved | Responded | A file from ISTS is expected early this week. Once existing approved ITAs are etered into IWDS 2.0, services can be updated.
Home Page | Scroll Bar Missing from Home Page | Bug | Not Started | Backlog Item Created
Assessments | TEA didn't save from answers saved on 7/9/2026. Assessment doesn't show in the Required section or the Assessments section. | Bug | Not Started | Backlog Item Created
Customer Settings | 2 customers she worked with last week are assigned to different LWIAS and she couldn't find them. | Bug | Not Started | Backlog Item Created
Applications | Application has some questions answered but they can't navigate through pages because some required fields are preventing them | Explanation | Resolved | Closed | Some questions are available to customers on the IwN side but others must be compelted by the Career Planner in 2.0
Customer Settings | Customer assigned to the wrong Career Planner but can't save when reassigned | Bug | Not Started | Backlog Item Created
Customer Settings | Customers assigned to old Career Planner and incorrect Worknet Center (Not even a LWIA office) | Explanation | Resolved | Response Still Needed | The example customers were not part of the migration. They have started new intakes some are in progress and will be assigned an LWIA when application is submitted. Others have already submitted and aligned with a different LWIA.
ITA | ITA requests weren't included in the hangfire file to ISTS on Friday. | Issue | In Progress | Response Still Needed
Eligiblity Certification | Unable to Certify for In School Youth | Explanation | Resolved | Closed | Customer did not trigger a barrier and they chose no regarding enrolling under the 5% so that is why ISY did not trigger.
Intake | Unable to submit application intake | Bug | Resolved | Released to Production
ETPL Relationships | Training Provider Relationship | Bug | Not Started | Backlog Item Created
Career Plan - Episodes | Episodes in 1.0 are only showing (1) Episode in 2.0 | Bug | Resolved | Released to Production
Missing Provider | Missing Provider Entity | Bug | Not Started | Backlog Item Created
Application Employment Zip | Zip Code Not Accepting those that start wtih Zero | Bug | Not Started | Backlog Item Created
Industry Classification | Incorrect Industry classification | Bug | Not Started | Backlog Item Created
Registered App | RAP Occupation / RTI Provider not Populating | Bug | Not Started | Backlog Item Created
Application | Unable to submit application intake | Bug | Resolved | Released to Production
Customer Settings | Customer assigned to wrong LWIA with no customer settings showing | Bug | Not Started | New
Missing Provider | Missing Provider Entity on GSA Ready to Enroll Page | Bug | In Progress | In Development
Career Plan | Private OJT service is using non-OJT template | Bug | Not Started | Backlog Item Created
Application | Can't open or sign Application - Access denied bug | Bug | Not Started | Response Still Needed
Career Plan | Can't choose LWIA isn't a service provider for Books Supportive service | Bug | Not Started | Backlog Item Created
Missing Provider | Missing Provider in Services Providing Entity Drop Down | Bug | Not Started | Backlog Item Created
Missing Provider | Missing Provider in Services Providing Entity Drop Down | Bug | Not Started | Backlog Item Created
Missing Provider | Missing Provider Entity on GSA Ready to Enroll Page | Bug | Not Started | Backlog Item Created
Intake | Career planner name not showing in the customer setting | Explanation | Resolved | Closed | User was assigned as "Front Line Suppor" role. To display in the Primary or Secondary Career Planner dropdown on customer settings the user has to have a Career Planner Role, Super User Role, or Data Steward Role.
Credentials | Entered/uploaded | Issue | Not Started | Response Still Needed
Career Plan - Dicont Status End Date | Can't add the Discontinuation Reason (End Date) | Bug | In Progress | In Development
HomePage | Career Planner's Home Page doesn't operate correctly | Issue | Not Started | Response Still Needed
Career Plan - Adding Service | Career Planner Can't Add A Service | Issue | Not Started | Response Still Needed
Goals,Steps, Services | Missing Associations | Bug | In Progress | In Development
Note on F151: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Miller, Olivia G this doesn't address the issue at hand. The problem is that Snelling Personnel Service isn't an LWIA and Maureen Flynn-Guttosch isn't a current Career planner.